## Sheet1
Page | Highlighted in RED | Action to take | Disposition | Review Notes
37 | FM_LVC1_CPU0_MEM23_MEMHOT_N | No change required. Change the color to normal. | done
37 | FM_LVC1_CPU0_MEM01_MEMHOT_N | No change required. Change the color to normal. | done
37 | CATERR_LVC1_CPU0_N | No change required. Change the color to normal. | done
37 | FM_LVC1_CPU0_THERMTRIP_N | No change required. Change the color to normal. | done
37 | PROCHOT_LVC1_CPU0_N | No change required. Change the color to normal. | done
37 | SVID_ALERT_N_CPU0 | No change required. Change the color to normal. | done
37 | SVID_SDIO_CPU0 | No change required. Change the color to normal. | done
37 | SVID_SCLK_CPU0 | No change required. Change the color to normal. | done
37 | R78 | Change the resistors R78 & R61 to 0402 pkg. | done
51 | Need to verify with RC team all test options can cause resonance | Note can be removed | done
82 | Need to verify with RC team all test options can cause resonance | Note can be removed | done
144 | Check Stargo P70 using different switch use 74CBT3383 | Done? | done
147 | VCC3p3_PS @ R151 pull up for HP_SLOT_PRSNT2_N | Remove the PU. No need because there is an internal PU on PRES_DET_N pin. | done
147 | Q2D1 FET | Replace the MOSFET with E55588-001 (same as Rose City). | done
147 | Q2D2 FET | Replace the MOSFET with E55588-001 (same as Rose City). | done
148 | Q6 transistor | Replace this part with a single Transistor MMBT3904 (C52245-001) | done
148 | VCC3p3_PS @ R897 pull up for HP_SLOT_3_MRL_SW_N | No Change required. Change the color to normal. | done
149 | Q3 transitor | OK. No change. | done
149 | Q6 transistor (2nd 1/2) | Use a single transistor device (C52245-001) | done
149 | R180 and Design note: connect to clock buffer | No change required. Change the color to normal. Also remove the design note. | done
149 | J2C1 and design note: header should be open or shorted | Leave it open. | done
200 | PCH0 Power enable Header message (duplicate ) | Just a information - change the color to white | done
201 | ACC0 Power enable Header message (duplicate ) | Just a information - change the color to white | done
202 | pch1 Power enable Header message (duplicate ) | Just a information - change the color to white ( need to add jumper table) | done
203 | ACC1 Power enable Header message (duplicate ) | Just a information - change the color to white | done
234 | need to check FPGA | The comment can be removed, but EN_VDDAB must be redisgned per Romley. | Removed note | Raj needs to finish ckt design for enable. ETA this week
234 | R9J14 | Change it to 165K | done | Pending IPN
235 | R2W3 | Change it to 63.4K | done
235 | R2W4 | Change it to 82.5K | done
235 | R1W5 | Change it to 63.4K | done
235 | CHANGE C1W2 TO 3300PF | Note can be removed | done
235 | CHANGE C2W4 TO 1500PF | Note can be removed | done
235 | CHECK TO SINAI (SIGNAL VDDAB_FB) | Remove the Note. | done
236 | Check for PG (PG_VDDQ_AB) | Remove the Note. | done
237 | Check FOR ncp5901 SUPPLY | Remove the Note. | done
237 | VCC5_PS_STBY | Change the color to Green | done
237 | CR1W1 | Make sure it is BAT54LT1 | confirmed in speed
237 | CR1W2 | Make sure it is BAT54LT1 | confirmed in speed
237 | C8J1 | No change required | DONE
237 | C8J2 | No change required | DONE
237 | C9J3 | No change required | DONE
237 | C9J4 | No change required | DONE
237 | R9H18 | No change required | DONE
238 | All caps on page 4v? | The cap values do not match with RC. Need to match with RC design. | DONE
238 | c7g1 | It is correct part… | DONE
238 | c7h6 | It is correct part….. | DONE
238 | r2v7 | Change it to 51ohm resistor with the same pkg size. | DONE | Pending IPN
238 | L8J1 needs to change to .22uh | Need to update the part to match RC. | DONE | Pending IPN
239 | Vcc3p3_ps two instances | Match with RC schematic…But, we have to discuss about this further….. | DONE | Keep as 3.3V_PS
239 | R1524 | Should be fine, but remove the OUT port which is not used (maintain the netname) | DONE | Keep net name - delete off-page arrow, no need for OPR. | Done
240 | C948 NOT on RC | No change required. Remove the comment and leave the 0.1uF. | done
240 | R7W29 | Looks fine.. Remove comment | done
240 | R7W30 | Looks fine.. Remove comment… Update the R4J13 to 210K. | done
240 | R7W31 | Change it to 165K | done | Pending IPN
240 | need to check FPGA | We need to discuss about this…. | ? | Need to verify the power sequence. Delete the Comment.
241 | R7Y5 | RC has this as 82.5k, 1% - verify with vendor | done | Pending IPN
241 | R3K5 need 63.4K | RC has these as 63.4k, 1% - verify with vendor | done | Pending IPN
241 | R3K6 need 63.4K | RC has these as 63.4k, 1% - verify with vendor | done | Pending IPN
241 | R6Y8 s/b 49.9K ohm empty | Change to 49.9k, empty | part not in library | Pending IPN
241 | Check to SINAI (SIGNAL VDDCD_FB) | no schmoo support - delete | done
242 | Check for PG | Appears to be OK | done
243 | Check FOR ncp5901 SUPPLY | This matches RC - recommend deleting comment; the 12V supply is filtered, | done | No comment
243 | VCC5_PS_STBY | This looks correct | done
243 | CR6W1 | these are the correct PN | done
243 | CR7W1 | these are the correct PN | done
243 | C1596 not on RC | Extra caps - leave in | done
243 | C1595 not on RC | Extra caps - leave in | done
243 | C6W6 | Match | done
243 | C9J4 | these are the wrong REF des, but the caps match on this page | done
243 | C7W11 | these are the wrong REF des, but the caps match on this page | done
243 | C7W12 | these are the wrong REF des, but the caps match on this page | done
243 | R4J2 | This matches | done
244 | L3J1 needs to change to .22uh | yes - change L3J1 to A61818-004 | done | Pending IPN
244 | R7V20 s/b 51 ohms | change to 51-Ohm, 1% | done | Pending IPN
244 | not on RC C280 | These match | done
244 | not on RC C281 | These match | done
245 | not on RC C966 | Extra caps - leave in | done
245 | not on RC C970 | Extra caps - leave in | done
245 | not on RC C974 | Extra caps - leave in | done
245 | not on RC C969, C3H8 on RC 2.2uf,0603 | These match | done | Leave as-is
245 | not on RC R704, R7V15 on RC empty 10K | PGOOD ckt is different, but OK - need to verify Shumway PS. | done | Keep net name - delete off-page arrow, no need for OPR.
245 | not on RC C985 | Extra caps - leave in | done
245 | Vcc3P3_PS | Does the DDR VTT Rail need to be active during S3? Verify with Architecture | done | Leave as 3.3V_PS
245 | Design Note: need to define vin 3.3v AUX or 3.3v | Does the DDR VTT Rail need to be active during S3? Verify with Architecture | done | Leave as 3.3V_PS
246 | C2213 (C987) | these match | done
246 | C2340 (C987) | these match | done
246 | need to check on FPGA | delete comment - this is checked by Raj | done
247 | R2161 change to 536 (R1261) | Change to 536-ohm to match RC | done | Pending IPN
247 | R1279 (R1211) | RC has these as 63.4k, 1% - verify with vendor | done | Pending IPN
247 | R1285(R1212) | RC has these as 63.4k, 1% - verify with vendor | done | Pending IPN
247 | Check to sinai (VDDEFG_FB) | Not supporting Sainia for feedback - delete comment | done
248 | C2204 Check for PG | This appears to be correct - it starts up the CPU VTT voltage | done
249 | Check FOR ncp5901 SUPPLY | This matches RC - recommend deleting comment; the 12V supply is filtered | done | No comment
249 | VCC5_PS_STBY | This looks correct | done
249 | CR7 | These are different part numbers from RC: RC using C83455-001 | DONE
249 | CR8 | These are different part numbers from RC: RC using C83455-001 | DONE
249 | R1253 | these match | DONE
249 | R1254 | these match | DONE
249 | R1249 | these match | DONE
249 | R1250 | these match | DONE
249 | C1119 | these match | DONE
249 | C1122 | these match | DONE
249 | C1121 | these match | DONE
249 | C1122 | these match | DONE
249 | R1260 | these match | DONE
251 | VCC3P3_PS | This appears to be correct. 3.3V is the pullup voltage | DONE
251 | delete pruple comments | NEW | Done
253 | Dcheck why need VCC3P3_aux enable by skt occupy | Matches RC - not sure why we need? No glitches? Also - it should be stuffed (its empty now). | done
253 | C8F27 | tolerance discrepency 10% vs. 20% | done
253 | C8F24 | tolerance discrepency 10% vs. 20% | done
d | Check why need AGRND for ViD1 | This matched RC - VID ties into VREF - may need to stay on same plane. VID0 -should ground to AGND??? | done
253 | R3R19 S/B 33K 5% | this is also on page 255, the RC uses 5% 33k, we have 1%. I'd say leave the 1% | done
253 | R3R23 S/B 33K 5% | this is also on page 255, the RC uses 5% 33k, we have 1%. I'd say leave the 1% | done
253 | Check design note | Delete this design note. No longer applies | done
254 | Delete blue design ntoes | NEW | done
255 | Dcheck why need VCC3P3_aux enable by skt occupy | Matches RC - not sure why we need? No glitches? Also - it should be stuffed (its empty now). | done
255 | Check why need AGRND for ViD1 | This matched RC - VID ties into VREF - may need to stay on same plane. VID0 -should ground to AGND??? | done
255 | Check control from FPGA | Appears to follow the IVB_SKT_OCC pin - looks correct | done
255 | Check design note | Delete this design note. No longer applies | done
256 | C3, C59, C58, C116 change to 724613-074 | RC is using these 470uF caps; look like POSCONs | done
257 | Check all en | Enable from CPU_VTT -> Enables DDR_VTT's and CPU_VSSA; seems okay??? | done
257 | R5K26 is 1% tol on RC 4.7K 15 is not standard | change to 1%, Speed bom A93550-392 is the 1% version of this part. Alternatively, change to 4.75k, 1% -> Standard part number | done
257 | C1212 not on RC | recommend leaving, but no-stuff - extra 0.1uF cap for VCC_F supply | done
258 | C5Y16 change to 0402 | RC - has 0402 in these locations. Everything looks OK - delete note. | done
258 | C5Y5 | RC - has 0402 in these locations. Everything looks OK - delete note. | done
258 | C5Y6 | RC - has 0402 in these locations. Everything looks OK - delete note. | done
258 | C5Y15 | RC - has 0402 in these locations. Everything looks OK - delete note. | done
258 | C5Y18 | RC - has 0402 in these locations. Everything looks OK - delete note. | done
259 | C5K2 check for PG | Seem's like these match - Feeds the PG loop; recommend deleting the note | done
259 | C5K1 check for PG | Seem's like these match - Feeds the PG loop; recommend deleting the note | done
259 | C5K6 S/B 560pf | RC - uses 560pf, verify with vendor and change | done | Pending IPN
259 | R5K8 S/B 2.61K Check 0603 | RC uses 2.61k, verify with vendor and change | done | Pending IPN
259 | Check to sinai (VCPU0_FB) | This optionally routes from the Sainai for voltage schmoo. Don't need to support Sainia on this interface; recommend delete this comment | done
260 | Check FOR ncp5901 SUPPLY | This matches RC - recommend deleting comment; the 12V supply is filtered, need filter on the 5V supply | done
260 | C1323 not on RC | recommend leaving, but no-stuff - extra 0.1uF cap for VCC_F supply | done
260 | C1324 not on RC | recommend leaving, but no-stuff - extra 0.1uF cap for VCC_F supply | done
260 | CR3Y1 | This part number matches RC, change color back to green | done
260 | CR4Y1 | This part number matches RC, change color back to green | done
260 | R5K22 S/B 127K | Verify with vendor - PWM3 has 127k pull down on RC. Recommend changing | done
260 | R3Y7 | Matches RC - change to green | done
260 | R3Y12 | Matches RC - change to green | done
260 | R4Y11 | Matches RC - change to green | done
260 | R4Y18 | Matches RC - change to green | done
260 | C3Y8 | These are on RC, change to green | done
260 | C3Y9 | These are on RC, change to green | done
260 | R3W4 | These are on RC, change to green | done
260 | C1339 not on RC | recommend leaving, but no-stuff - extra 22uF cap for output | done
260 | C1340 not on RC | recommend leaving, but no-stuff - extra 22uF cap for output | done
260 | R4Y17 | Need to add filter reisistor to the 5V supply on the NCP5901 | done | Disregard
261 | Check for NCP5901 Supply | This matches RC - recommend deleting comment; the 12V supply is filtered | done
261 | CR4Y2 | This part number matches RC, change color back to green | done
261 | CR4Y3 | This part number matches RC, change color back to green | done
261 | C1304 not on RC | recommend leaving, but no-stuff - extra 0.1uF cap for VCC_F supply | done
261 | C1303 Not on RC | recommend leaving, but no-stuff - extra 0.1uF cap for VCC_F supply | done
261 | R4Y12 | These are on RC, change to green | done
261 | R4Y13 | These are on RC, change to green | done
261 | R4Y19 | These are on RC, change to green | done
261 | R4Y20 | These are on RC, change to green | done
261 | C4Y10 | These are on RC, change to green | done
261 | C4Y11 | These are on RC, change to green | done
261 | C4Y13 | These are on RC, change to green | done
261 | C4Y14 | These are on RC, change to green | done
261 | R4W12 | These are on RC, change to green | done
261 | C1319 Not on RC | recommend leaving, but no-stuff - extra 22uF cap for output | done
261 | C1320 Not on RC | recommend leaving, but no-stuff - extra 22uF cap for output | done
262 | R5Y25 S/B 255K | Change to 255k, empty | part not in library | Pending IPN
262 | C5Y9 Check 3900pf | change to 3900pf | done
263 | C1268 not on RC | not on RC, recommend leaving, but no-stuff | done
263 | R5J9 value | this should be 51-ohm | part not in library | Pending IPN
264 | Check for NCP5901 supply | This matches RC - recommend deleting comment; the 12V supply is filtered | done
264 | Cr4Y4 | This part number matches RC, change color back to green | done
264 | C1253 NOT ON RC | recommend leaving, but no-stuff - extra 0.1uF cap | done
264 | C1249 not on RC | recommend leaving, but no-stuff - extra 0.1uF cap | done
264 | C1250 not on RC | recommend leaving, but no-stuff - extra 0.1uF cap | done
264 | R5Y4 | These are on RC, change to green | done
264 | R5Y9 | These are on RC, change to green | done
264 | C5Y15 | These are on RC, change to green | done
264 | C5Y3 | These are on RC, change to green | done
264 | R5J5 S/B 51 ohm | should be 51-ohm | part not in library | Pending IPN
264 | C1268 NOT ON RC | recommend leaving, but no-stuff - extra 0.1uF cap | done
265 | Check all EN | Appears correct | done
267 | C2029 Check for PG | Appears correct | done
267 | C2028 Check for PG | Appears correct | done
268 | Check for NCP5901 supply | This matches RC - recommend deleting comment; the 12V supply is filtered | done
268 | CR18 | recommend leaving, but no-stuff - extra 0.1uF cap | ? | Leave as-is; keep HC cap's
268 | CR19 | recommend leaving, but no-stuff - extra 0.1uF cap | ? | Leave as-is; keep HC cap's
268 | R1982 check 127K | change to 127k | done
268 | R1819 | These are on RC, change to green | done
268 | R1820 | These are on RC, change to green | done
268 | R1823 | These are on RC, change to green | done
268 | R1824 | These are on RC, change to green | done
268 | C1696 | These are on RC, change to green | done
268 | C1699 | These are on RC, change to green | done
268 | R1830 | These are on RC, change to green | done
268 | C1698 | These are on RC, change to green | done
268 | C1700 | These are on RC, change to green | done
269 | Check for NCP5901 supply | This matches RC - recommend deleting comment; the 12V supply is filtered | done
269 | CR16 | Different PN's from RC - align with RC | RC or HC | Align with HC - disregard comment
269 | CR17 | Different PN's from RC - align with RC | RC or HC | Align with HC - disregard comment
269 | R1795 | These are on RC, change to green | done
269 | R1796 | These are on RC, change to green | done
269 | R1799 | These are on RC, change to green | done
269 | R1800 | These are on RC, change to green | done
269 | R1806 | These are on RC, change to green | done
269 | C1678 | These are on RC, change to green | done
269 | C1680 | These are on RC, change to green | done
269 | C1676 | These are on RC, change to green | done
269 | C1679 | These are on RC, change to green | done
270 | C1757 CHECK 3900PF | Change to 3900pf | done
270 | R1978 Check 255k 0402 | change to 255k, 402 | part not in library | Pending IPN
270 | R1784 | change to 82.5k, 1% | done
271 | C1636, C1639, C1643, C1646, C1649, C1652 | These now match - ok
272 | Check for NCP5901 supply | This matches RC - recommend deleting comment; the 12V supply is filtered
272 | CR15 | Different PN's from RC - align with RC |  | Align with HC - disregard comment
272 | R1771 | These are on RC, change to green
272 | R1772 | These are on RC, change to green
272 | C1628 | These are on RC, change to green
272 | C1630 | These are on RC, change to green
272 | C1622 | This is actually C1623 - change to 470 to match RC |  | Align with HC - disregard comment
274 | L19 | this is not the same PN as RC, recommend changing to match |  | Align with HC - disregard comment
274 | Q47 | Different PN's from RC - is OK since it's a smalls ignal control. |  | Align with HC - disregard comment
282 | Change 5v should be 5v or 5v stby (All supplies on page) | Good question - I think they should be 3.3V, Raj? |  | Keep as 3.3V_PS - no change
283 | VCC3P3_AUX | This should be STBY? Raj? |  | Change to VCC3P3_PS
283 | signal name DIR_P273 | no issue here, chane to orange | done
283 | signal name GLTREF_P273 | no issue here, chane to orange | done
291 | signal name PCH_SYS_PWROK | This looks correct - we need a through review of the power sequence options
291 | signal name PCH0_SYS_PWROK | This looks correct - we need a through review of the power sequence options
291 | signal name PCH1_SYS_PWROK | This looks correct - we need a through review of the power sequence options
297 | signal name CATERR_LVC1_CPU0_N | These look right - verify this is OD signal and the overall options for the board |  | no change - correct
297 | signal name CATERR_LVC1_CPU1_N | These look right - verify this is OD signal and the overall options for the board |  | no change - correct
297 | signal name CATERR_CPU_N | These look right - verify this is OD signal and the overall options for the board |  | no change - correct
297 | R68 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | R69 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | R70 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | R71 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | R72 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | R73 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | R1111 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | R1112 | This looks right - veriffy the overall architecture for the board. |  | no change - correct
297 | Check on Power rail | Yes - this QS should be powered with 5V |  | Change GTL2005 (U3) to VCC3P3_PS
297 | (4) off pages (out) | This looks right - veriffy the overall architecture for the board.
297 | TO GPIO FOR PCH0 AND PCH1, ALL GPIO NEED PULL-UP? ALL GPIO ON CORE WELL? | Yes - GP18, GP20, GP34 are all Core well and require a pull-up; delete note | done
299 | signal name PECI_CPU | Looks fine - change to orange | done
299 | signal name PECI_CPU_R | Looks fine - change to orange | done
302 | 3.3 AUX but pull by VTT_CPU1 get from Harbor city P49 | Great question??? |  | Change _AUX to _PS on all 3P3, fix 4-way junction off of pin 14 of U222
302 | VCC3P3_AUX | Great question??? |  | Change _AUX to _PS on all 3P3, fix 4-way junction off of pin 14 of U222
302 | DS3 | I like the RED color. |  | Change to Yellow LED's
302 | DS9 | I like the RED color. |  | Change to Yellow LED's
302 | FM_LVC3_SKT1_IVB_OCC_N GO TO gpio CPH1 | We have a 10k and 4.7k PU/PD on thie FM_LVC1_SKT1_IVB_OCC_N net - otherwise it looks OK |  | remove comments - empty R1113, R839
302 | R1135 has issues with the wire overlap and the text placement overlap | Fix | done
310 | U81 check update with XOR | I think we want an XOR gate here. Change. |  | Find XOR gate in library, add label "PCH CFG ERROR"

## Sheet2
Page | Highlighted in RED | Action to take | Disposition
234 | need to check FPGA | The comment can be removed, but EN_VDDAB must be redisgned per Romley. | Removed note
234 | R9J14 | Change it to 165K | part not in library
238 | r2v7 | Change it to 51ohm resistor with the same pkg size. | part not in library
238 | L8J1 needs to change to .22uh | Need to update the part to match RC. | part not in library
239 | Vcc3p3_ps two instances | Match with RC schematic…But, we have to discuss about this further….. | RC is P3V3_AUX
239 | R1524 | Should be fine, but remove the OUT port which is not used (maintain the netname) | ?
240 | R7W31 | Change it to 165K | part not in library
240 | need to check FPGA | We need to discuss about this…. | ?
241 | R7Y5 | RC has this as 82.5k, 1% - verify with vendor | part not in library
241 | R3K5 need 63.4K | RC has these as 63.4k, 1% - verify with vendor | part not in library
241 | R3K6 need 63.4K | RC has these as 63.4k, 1% - verify with vendor | part not in library
241 | R6Y8 s/b 49.9K ohm empty | Change to 49.9k, empty | part not in library
243 | Check FOR ncp5901 SUPPLY | This matches RC - recommend deleting comment; the 12V supply is filtered, need filter on the 5V supply | filter P238
244 | L3J1 needs to change to .22uh | yes - change L3J1 to A61818-004 | part not in library
244 | R7V20 s/b 51 ohms | change to 51-Ohm, 1% | part not in library
245 | not on RC C969, C3H8 on RC 2.2uf,0603 | These match
245 | not on RC R704, R7V15 on RC empty 10K | PGOOD ckt is different, but OK - need to verify Shumway PS.
245 | Vcc3P3_PS | Does the DDR VTT Rail need to be active during S3? Verify with Architecture
245 | Design Note: need to define vin 3.3v AUX or 3.3v | Does the DDR VTT Rail need to be active during S3? Verify with Architecture
247 | R2161 change to 536 (R1261) | Change to 536-ohm to match RC | part not in library
247 | R1279 (R1211) | RC has these as 63.4k, 1% - verify with vendor | part not in library
247 | R1285(R1212) | RC has these as 63.4k, 1% - verify with vendor | part not in library
249 | Check FOR ncp5901 SUPPLY | This matches RC - recommend deleting comment; the 12V supply is filtered, need filter on the 5V supply
259 | C5K6 S/B 560pf | RC - uses 560pf, verify with vendor and change | part not in library
259 | R5K8 S/B 2.61K Check 0603 | RC uses 2.61k, verify with vendor and change | part not in library
260 | R4Y17 | Need to add filter reisistor to the 5V supply on the NCP5901
262 | R5Y25 S/B 255K | Change to 255k, empty | part not in library
263 | R5J9 value | this should be 51-ohm | part not in library
264 | R5J5 S/B 51 ohm | should be 51-ohm | part not in library
268 | CR18 | recommend leaving, but no-stuff - extra 0.1uF cap | ?
268 | CR19 | recommend leaving, but no-stuff - extra 0.1uF cap | ?
268 | R18982 check 127K | change to 127k
269 | CR16 | Different PN's from RC - align with RC | RC or HC
269 | CR17 | Different PN's from RC - align with RC | RC or HC
270 | R1978 Check 255k 0402 | change to 255k, 402 | part not in library
272 | CR15 | Different PN's from RC - align with RC
272 | C1622 | This is actually C1623 - change to 470 to match RC
274 | L19 | this is not the same PN as RC, recommend changing to match
274 | Q47 | Different PN's from RC - is OK since it's a smalls ignal control.
282 | Change 5v should be 5v or 5v stby (All supplies on page) | Good question - I think they should be 3.3V, Raj?
283 | VCC3P3_AUX | This should be STBY? Raj?
283 | signal name DIR_P273 | no issue here, chane to orange
283 | signal name GLTREF_P273 | no issue here, chane to orange
291 | signal name PCH_SYS_PWROK | This looks correct - we need a through review of the power sequence options
291 | signal name PCH0_SYS_PWROK | This looks correct - we need a through review of the power sequence options
291 | signal name PCH1_SYS_PWROK | This looks correct - we need a through review of the power sequence options
297 | signal name CATERR_LVC1_CPU0_N | These look right - verify this is OD signal and the overall options for the board
297 | signal name CATERR_LVC1_CPU1_N | These look right - verify this is OD signal and the overall options for the board
297 | signal name CATERR_CPU_N | These look right - verify this is OD signal and the overall options for the board
297 | R68 | This looks right - veriffy the overall architecture for the board.
297 | R69 | This looks right - veriffy the overall architecture for the board.
297 | R70 | This looks right - veriffy the overall architecture for the board.
297 | R71 | This looks right - veriffy the overall architecture for the board.
297 | R72 | This looks right - veriffy the overall architecture for the board.
297 | R73 | This looks right - veriffy the overall architecture for the board.
297 | R1111 | This looks right - veriffy the overall architecture for the board.
297 | R1112 | This looks right - veriffy the overall architecture for the board.
297 | Check on Power rail | Yes - this QS should be powered with 5V
297 | (4) off pages (out) | This looks right - veriffy the overall architecture for the board.
297 | TO GPIO FOR PCH0 AND PCH1, ALL GPIO NEED PULL-UP? ALL GPIO ON CORE WELL? | Yes - GP18, GP20, GP34 are all Core well and require a pull-up; delete note
299 | signal name PECI_CPU | Looks fine - change to orange
299 | signal name PECI_CPU_R | Looks fine - change to orange
302 | 3.3 AUX but pull by VTT_CPU1 get from Harbor city P49 | Great question???
302 | VCC3P3_AUX | Great question???
302 | DS3 | I like the RED color.
302 | DS9 | I like the RED color.
302 | FM_LVC3_SKT1_IVB_OCC_N GO TO gpio CPH1 | We have a 10k and 4.7k PU/PD on thie FM_LVC1_SKT1_IVB_OCC_N net - otherwise it looks OK
302 | R1135 has issues with the wire overlap and the text placement overlap | Fix
310 | U81 check update with XOR | I think we want an XOR gate here. Change.